| N | Месяц (Month) | Блок | Deliverable / Task | Результат (Result) | Partner |
| --- | --- | --- | --- | --- | --- |
|  | M2 | Dessimination and Exploration | D6.2 Dissemination plan | Detailed dissemination plan (PDF/English | SILKROAD Document, report |
|  | M3 | Quality plan: Evaluation and Improvement | D5.1 Quality Assurance and Contingency Plan | Comprehensive Quality Assurance (QA) plan outlining procedures, methods, and tools to be applied throughout the project lifecycle Definition of quality indicators for deliverables, milestones, and project outcomes Risk assessment carried out at the proposal stage and continuously updated during project implementation Contingency measures designed to address potential risks and ensure smooth project execution Responsibilities of internal and external stakeholders in monitoring project quality and contingency arrangements Mechanisms for continuous feedback, corrective actions, and reporting Appendices: QA templates, risk assessment matrix, contingency measures table, monitoring forms | UNIKOZ KokSU Document, report |
|  | М4 | Project management | D1.1 Отчет о запуске проекта (Report on Kick-off Meeting) | Objectives of the project and meeting outcomes Results and agreed tasks for each Work Package Project coordination procedures and overall project timeline Agenda of the kick-off meeting Attendance list (with signatures) Minutes of the meeting Evidence: photos, videos, presentations (PDF/ English) | KokSU Document, report |
|  | M4 | Project management | D1.1 Management and Communication Manual | Document outlining the project management and communication procedures and tools, calendar | KokSU Document, report |
|  | M5 | Capacity building of staff Академическое направление | D2.1Training plan | Detailed plan of the organization and delivery for both online and onsite trainings, their objectives and expected impacts (PDF/English). | UPT Document, report |
|  | M6 | Dessimination and Exploration | D6.1 Project webpage | DIANA webpage Websites, patent filings, videos, etc | SILKROAD |
|  | M16 | Capacity building of staff Академическое направление | D2.2 Report on deivered online trainings | Training programme and agenda Dates of implementation List of attendants (with personal data protected according to GDPR rules) Training materials used during the online sessions Summary of training activities and outcomes Evaluation and feedback from participants Recommendations for future training activities Appendices: agendas, participant lists, training materials, evaluation forms, feedback summaries (PDF/English) | UPT Document, report |
|  | M18 | Project management | D1.3 Interim Report | Overview of project implementation during the first 18 months Progress achieved towards objectives and expected results Summary of activities conducted by each partner Description of deliverables produced and milestones reached Financial and administrative overview Challenges encountered and mitigation measures taken Evaluation of dissemination and communication activities Appendices: agendas, attendance lists, reports, photos (where applicable) Dissemination level: contains personal and institutional data | KokSU Document, report |
|  | M18 | Quality plan: Evaluation and Improvement | D5.2 Implementation of the Quality Assurance Plan at mid-term | Interim evaluation of project progress compared with the baseline plan and expected outcomes Collection of feedback from WP leaders, partners, and individual performers through structured communication (meetings, surveys, reports) Identification of emerging and potential problems or risks affecting implementation Analysis of corrective measures and adjustments needed to ensure timely achievement of objectives Review of deliverables, milestones, and project management processes up to the mid-stage Recommendations for improvements to enhance efficiency, risk management, and quality assurance in the second half of the project Appendices: Meeting minutes, evaluation tools, feedback forms, comparison tables of planned vs. achieved results | UNIKOZ KokSU Document, report |
|  | M18 | Dessimination and Exploration | D6.3 Implementation of the Dissemination Plan at mid-term | o provide an overview of the Dissemination Plan and its objectives. To demonstrate the progress of implementation by M18, including activities, tools, and communication channels used. To describe the development and application of the project’s visual identity package (logo, templates, guidelines). To present the design, validation, and distribution of dissemination materials. To define branding guidelines for internal and external communication. To provide concrete examples of usage in reports, presentations, the project website, and social media. To evidence the adoption of the visual identity and dissemination practices by partners across different channels. To assess the effectiveness of dissemination actions at mid-term and outline recommendations for further improvement. Appendices: Graphic files and templates. Screenshots and examples of dissemination activities (reports, website, social media posts, presentations). Summary tables of dissemination outputs by partners. (PDF/English) | SILKROAD Document, report |
|  | M19 | Capacity building of staff Академическое направление | D2.3 Report on delivered onsite training | Training programme and agenda Dates and locations of onsite trainings List of attendants (with personal data protected according to GDPR rules) Training materials used during the onsite sessions Summary of training activities and outcomes Evaluation and feedback from participants Recommendations for improvement and replication Appendices: agendas, participant lists, training materials, evaluation forms, feedback summaries (PDF/English) | UPT Document, report |
|  | M19 | Capacity building of staff Академическое направление | D2.4 Roadmap | Comprehensive roadmap with recommendations to improve the quality, relevance, and effectiveness of educational programs in the tourism sector at PC-HEIs, with a special focus on rural tourism entrepreneurship Guidance on integrating outcomes of trainings and study visits into curricula Suggestions for innovative teaching and learning approaches to foster entrepreneurship in rural tourism Recommendations for aligning curricula with labour market needs, stakeholder feedback, and sustainability goals Practical steps for embedding the roadmap results into the modules developed under WP3 (“Designing the course Rural tourism entrepreneurship”) Appendices: training outcomes, study visit insights, stakeholder feedback, supporting data and reference materials (PDF/English) | KazAST Document, report |
|  | M19 | Capacity building of staff Академическое направление | D2.5 Guidelines on Women Empowerment and Skills Enhancement | Guidelines with recommendations on women empowering and skills enhancement (PDF/English) | NSTU Document, report |
|  | M20 | Designing the course Rural Tourism | D3.1 Report of reviewed programmes | Detailed report of reviewed programmes at all PC-HEIs (PDF/English) | HSW Document, report |
|  | M25 | Designing the course Rural Tourism Академическое направление | D3.2 Development of Course “Rural Tourism Entrepreneurship” – Students | Jointly designed tailor-made course “Rural Tourism Entrepreneurship” for HEI students Curricula: 5 ECTS, including 4 modules: Rural tourism and its relationship with other types of tourism Introduction to entrepreneurship fundamentals and principles Rural tourism and climate change Innovation in rural tourism Syllabus and learning outcomes: Aligned with HEI educational standards; development of entrepreneurial skills for effective project design in rural tourism Training materials: Presentations, case studies, simulation tasks, interactive methods (entrepreneurial duels, brainstorming, situational workshops, pitches) Accreditation: To be submitted for approval at each HEI faculty/department in line with national regulations Outputs: 1 course per HEI (7 courses total, adapted to local contexts, best practices, and examples of rural entrepreneurs) (PDF/English) | HSW Document, report |
|  | M26 | Designing the course Rural Tourism Академическое направление | D3.3 Development of Course “Rural Tourism Entrepreneurship” – Adults | Jointly designed tailor-made course “Rural Tourism Entrepreneurship” for adult learners, especially women in rural areas Curricula: 5 ECTS equivalent workload, structured into 4 modules (same as for students), adapted for non-formal adult education Syllabus and learning outcomes: Focus on practical entrepreneurial competences, creativity, and self-employment in rural tourism Training materials: Accessible learning resources, case studies, interactive workshops, mentoring, group projects, real-life simulation of business management tasks Inclusivity: Special attention to women’s empowerment and opportunities for women with disabilities (accessible materials, additional support) Outputs: 1 course per HEI (7 courses total, designed for adult learners, adapted to local needs and socio-economic conditions) (PDF/English) | HSW Document, report |
|  | M30 | Students enrolment and course implementation of Rural Tourism Enterpreneurship course | D4.1 Report on Selection, Recruitment, and Implementation of Rural Tourism Entrepreneurship course | Programme of entrepreneurial training (agenda, modules, trainers) Dates, locations, and delivery format (in-person/online) Number and profile of students/adults enrolled/% of female Training materials used (curricula, manuals, case studies) Report on implementation (participation, engagement, challenges) Evaluation and feedback from participants Evidence: attendance lists, photos, videos, training reports (PDF/English) | EKTU Documents, report |
|  | M33 | Students enrolment and course implementation of Rural Tourism Enterpreneurship course | D4.2 Report on Entrepreneurial projects | Description of entrepreneurial projects developed by students and adults Project topics, objectives, and methodology Profiles of participating teams (students/adults/mentors) Implementation timeline and activities Outputs of projects (business plans, prototypes, pilot initiatives) Evaluation of projects (criteria, feedback from mentors and external reviewers) Lessons learned and recommendations for further entrepreneurship initiatives (PDF/English) | EKTU Documents, report |
|  | M34 | Dessimination and Exploration | Final conference report | Final conference report (PDF/English) | SILKROAD Documents, report |
|  | M36 | Project management | D1.4 Report on Impact and Sustainability | Document presenting the impact and sustainability of the project (PDF/English) | HSW Document, report |
|  | M36 | Quality plan: Evaluation and Improvement | D5.3 Implementation of the Quality Assurance Plan at the end of the project | Procedures and tools applied for project quality monitoring at mid-term Internal evaluation reports and feedback from partners Results of surveys/questionnaires on project implementation quality Recommendations for improvement and corrective measures Evidence of quality assurance activities (meeting notes, evaluation forms, reports) Appendices: evaluation templates, aggregated data, feedback summaries (PDF/ English) | UNIKOZ KokSU Document, report |
|  | M36 | Dessimination and Exploration | D6.4 Outreach Materials | Collection of project outreach materials developed throughout the project. Flyers, brochures, newsletters, posters, roll-ups, and other promotional content Digital communication outputs (social media posts, infographics, press releases) Materials adapted for different target groups (students, teachers, policymakers, stakeholders) Evidence of dissemination and outreach activities (photos, distribution records, statistics) Evaluation of the effectiveness of outreach strategies Appendices: copies of materials, media coverage links, screenshots (PDF/English) | SILKROAD Document, report |

Project Management from KokSU: Ryspaeva Dinara, Baikenova Gulima, Bermaganbetova Lyazzat
Project management (General project coordination)

Quality Plan: Evaluation and Improvement
Capacity Building of Staff

Academic Work Package from KokSU : Rakisheva Gulmira, Evloeva Aza, Sabitova Diana.
Designing the Course “Rural Tourism”
Students’ Enrolment and Implementation of the Course “Rural Tourism Entrepreneurship”

Dissemination from KokSU – Sabitova Diana, Belgibaeva Anargul, Evloeva Aza.
Dissemination and Exploitation of Results
Quality Plan: Evaluation and Improvement